## TimeLine
DATE | TIMELINE ITEM
2002-05-03 | Closed on Construction Loan
2002-05-06 | Lot 70 Staked
2002-05-14 | Basement dug
2002-05-15 | Basement footers poured
2002-05-21 | Basement walls poured
2002-05-23 | Basement floor poured
2002-05-24 | Crawl & garage footers poured
2002-05-29 | Crawl & garage foundation block laid
2002-06-03 | Foundation back-filled and trees up-rooted
2002-06-04 | Garage floor concrete poured
2002-06-07 | Framing started
2002-06-12 | First floor walls begun
2002-06-14 | First floor walls completed
2002-06-20 | Roof rafters started
2002-07-01 | Roof framing & decking complete
2002-07-02 | Exterior trim, windows, doors started
2002-07-09 | Exterior trim, windows, doors completed
2002-07-09 | Plumbing started
2002-07-10 | HVAC started
2002-07-11 | Shingle application started
2002-07-11 | Framing complete (except bulkheads)
2002-07-15 | HVAC complete, electric wiring started
2002-07-18 | Brick delivered, roofing 70% complete
2002-07-21 | Cat5e/phone/security/audio wiring started
2002-07-24 | Electric wiring rough-in complete
2002-07-25 | Roofing (shingle application) complete
2002-07-29 | Cat5e/phone/security/audio wiring completed
2002-07-29 | Catastrophe! Retaining wall collapses from rain
2002-07-30 | Plumbing complete
2002-07-31 | Bricklayers begin to lay brick
2002-08-06 | Framers compete bulkhead framing
2002-08-08 | Framers repair wall damaged in wall collapse
2002-08-09 | Insulators begin insulation
2002-08-10 | All wall insulation complete (ceilings done later)
2002-08-12 | Brick is complete
2002-08-14 | Drywall hanging started
2002-08-21 | Rain gutters installed
2002-08-26 | Drywall hanging complete
2002-08-27 | Drywall finishing under way
2002-08-27 | Rough grade completed / sidewalks cut
2002-09-03 | Ceilings textured
2002-09-03 | Driveway/sidewalk forming begun
2002-09-04 | Drywall finishing completed
2002-09-04 | Water turned on for first time
2002-09-10 | Trim application started
2002-09-13 | Driveways and sidewalks complete
2002-09-20 | Trim application completed
2002-09-24 | Interior painting started
2002-09-25 | Downspout drains installed
2002-09-26 | Finish grade completed
2002-09-27 | Lawn irrigation system installed
2002-09-28 | Landscaping started
2002-10-02 | Tile flooring installation begun
2002-10-03 | Landscaping complete
2002-10-08 | Final electrical started
2002-10-09 | Tile flooring completed
2002-10-10 | Sod installation begun
2002-10-11 | Sod installation complete
2002-10-11 | Final plumbing started
2002-10-16 | Furnace fired for first time
2002-10-17 | Carpet install begun
2002-10-19 | Kitchen cabinets installed
2002-10-19 | Power turned on for first time
2002-10-22 | Final trim finish under way
2002-10-24 | Final electrical continues
2002-10-27 | Exterior camera system installed
2002-10-28 | Kitchen countertops intalled
2002-10-28 | Final plumbing complete
2002-10-29 | Blind hanging under way
2002-11-01 | Blind hanging finished
2002-11-04 | Final inspection
2002-11-05 | Final insulation completed in attic
2002-11-06 | Final trim completed
2002-11-08 | Apartment move-out started
2002-11-09 | Moving Day!